## Jun25-Jun29
Daily Stand-up Meeting Report
Week: Jun 25 - Jun 29
Project Name: Socio Analyzer
Team Name: MI7
| Monday | Tuesday | Wednesday | Thursday | Friday
Abhijeet Agrawal | 1) | 1) | 1) Prepared handouts for NodeJS version script | 1) Started working on API's in NodeJS | Mid term presentation given and feedback recieved
| 2) | 2) | 2) Prepared installation guide for Demo | 2) Worked on Prototype creation
| 3) | 3) | 3) Supporting for Python Version script development | 3) Working on exploring sentimental analysis stuff
Durga Charan Potukuru | 1) | 1) | 1) Worked on tools and technologies part of my presentation | 1)developed the single page working software for mid term presentation
| 2) | 2) | 2) Working software and also sentiment analysis | 2) sentiment analysis and presentation
| 3) | 3) | 3) No impediments | No impediments
Krishnaveni Karri | 1) | 1) | 1)worked on data retrival using python | 1) Reseached on sentiment analysis
| 2) | 2) | 2) study about sentiment analysis and make work flow digram as a part of presentation | 2) Work on presentation
| 3) | 3) | 3) No impediments | 3) no impediments
Sai Praneetha Jaladanki | 1) | 1) | 1) Completed second requirements draft | 1) Worked on mid term presentation, edited requirements draft according to feedback
| 2) | 2) | 2) Working on problem statement and proposed solution | 2) Practice mid term presentation, study the client requirements from today's meeting
| 3) | 3) | 3) No impediments | 3) No impediments
Srinivas Pakala | 1) | 1) | 1) Explored on how to design a good prototype | 1) Done with designing of a prototype
| 2) | 2) | 2) Working on design of a prototype | 2) Need to work on presentation slides
| 3) | 3) | 3) No impediments | 3) No impediments
Vipul Chandoor | 1) | 1) | 1) Collecting vocabulary for introduction image | 1) Created a image for introduction. Collected some data for mid term presentation
| 2) | 2) | 2) Completing the image for presentaion | 2) Should prepare for mid term presentation
| 3) | 3) | 3) No impediments | 3) No impediments
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Jul2-Jul6
Daily Stand-up Meeting Report
Week: Jul 2 - Jul 6
Project Name: Socio analyzer
Team Name: MI7
| Monday | Tuesday | Wednesday | Thursday | Friday
Abhijeet Agrawal | 1)Created sample app using Flask framework in Python | 1)Deployed angular and flask sample apps to heroku | 1) | 1) | 1)
| 2) Working on deploying the angular and flask app on Heroku | 2)Working on establish the database connectivity in Flask | 2) | 2) | 2)
| 3)No imediments | 3)No imediments | 3) | 3) | 3)
Durga Charan Potukuru | 1) Explored ways to trigger python script from angular | 1)Worked on paralleldots api for emotions in the text | 1) | 1) | 1)
| Explore more about them and collect the data that we got from our script and save them | 2)Will be working on saving the subjectivity and polarity of the tweet | 2) | 2) | 2)
| No impediments | 3)No impediments | 3) | 3) | 3)
Krishnaveni Karri | 1) started working on sentiment analysis using different apis | 1)created model for the project | 1) | 1) | 1)
| 2)create model for the project | 2) intergrate model with Flask code | 2) | 2) | 2)
| 3) No impediments | 3)no impediments | 3) | 3) | 3)
Sai Praneetha Jaladanki | 1) Exploring more on sentiment analysis | 1) Learned about APIs in Python | 1) | 1) | 1)
| 2) Learn about APIs in Python | 2) Explored more on D3.js graphs | 2) | 2) | 2)
| 3) No impediments | 3) No impediments | 3) | 3) | 3)
Srinivas Pakala | 1) Watching videos on how to use D3.js | 1) Generate some graphs using D3.js | 1) | 1) | 1)
| 2) More on d3.js and API's in python. | 2) Working to generate graphs for real data that we have generated. | 2) | 2) | 2)
| 3) No Impediments | 3) No impediments. | 3) | 3) | 3)
Vipul Chandoor | 1) Learning basic python | 1) Worked on removal of regular expression from tweets | 1) | 1) | 1)
| Research and Learning on API's | 2) Should work on Integration of angular and d3.js | 2) | 2) | 2)
| 3) No Impediments | 3) No Impediments | 3) | 3) | 3)
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Jul9-Jul13
Daily Stand-up Meeting Report
Week: Jul 9 - Jul 13
Project Name: Socio analyzer
Team Name: MI7
| Monday | Tuesday | Wednesday | Thursday | Friday
Abhijeet Agrawal | 1)Integrated the database connectivity code in Flask API | 1)Worked on UI design, developed some pages | 1)
| 2)Started working on builing UI using Angular | 2)Exploring the custom classifers in blob. | 2)
| 3)No imediments | 3)Prepare the presentation slides for textblob | 3)
Durga Charan Potukuru | 1) worked on generation of polarity and subjectivity for individual tweets | 1)worked on the script for sentiment analysis using paralleldots and also my part of the presentation | 1)
| 2) Have to work on the script for sentiment analysis using paralleldots | 2) Have to work on the slides and should prepare for the final presentation | 2)
| No impediments | 3) No impediments | 3)
Krishnaveni Karri | 1)worked on get and post methods | 1)designed the workflow | 1)
| 2) design a workflow for the project | 2)work on final presentation | 2)
| 3)No impediments | 3)No impediments | 3)
Sai Praneetha Jaladanki | 1) Designing of graphs using various input formats like .csv, .json Worked on a historical dataset Using javascript to generate graphs Exploring more on what graphs required for the project | 1)Finalizing graphs for the project Working on final presentation Editted the mid term presentation according the feedback | 1)
| 2) Finalizing the graphs Exploring graphs for pilot project | 2)Final presentation Developing problem statement and solution | 2)
| 3) No impediments | 3) No impediments | 3)
Srinivas Pakala | 1) Explored on how to generate different graphs | 1) Explored a little about sentiment 140 API. | 1)
| 2) Need to work on how to generate 3D graphs for our project | 2) Need to work on the presentation slides | 2)
| 3) No impediments | 3) No impedements | 3)
Vipul Chandoor | 1) Integration of D3js and Angular with sample output with 2D graphs | 1) Research and sample code for AYLIEN | 1)
| 2) Should work on 3D graphs then integrating it with angular | 2)Should work on Presentation slides | 2)
| 3) Unable to work on 3D graphs | 3) No impediments | 3)
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Aug
Daily Stand-up Meeting Report
Week:
Project Name: Socio analyzer
Team Name: MI7
| Monday | Tuesday | Wednesday | Thursday | Friday
Abhijeet Agrawal | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Durga Charan Potukuru | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Krishnaveni Karri | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Sai Praneetha Jaladanki | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Srinivas Pakala | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Vipul Chandoor | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Master File
Daily Stand-up Meeting Report
Week:
Project Name: Socio analyzer
Team Name: MI7
| Monday | Tuesday | Wednesday | Thursday | Friday
Abhijeet Agrawal | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Durga Charan Potukuru | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Krishnaveni Karri | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Sai Praneetha Jaladanki | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Srinivas Pakala | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Vipul Chandoor | 1) | 1) | 1)
| 2) | 2) | 2)
| 3) | 3) | 3)
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?